## Sheet1
Week 7 | Tasks | Task Allocation | Notes
| Client Meeting | All Team Members | 29/08, 1:30pm at clients work
| Mentor Meeting | All Team Members | Held on 24/08 in person
| Lecture | All Team Members | Not able to attend due to client meeting but notes to be reviewed
| Team Portfolio | All Team Members | Continue to contribute / setup the Github
| Team Poster | All Team Members | Start drafting background information sections
| Individual Reports | All Team Members | Start drafting individually
| Taking videos for model training | All Team Members | 02/09, 2pm taking videos with pi and PPE gear
| Data labeling & drawing diagrams | Julia | Data labeling videos for model, drawing package diagram
| Github and mounting of camera onto the body | Gamana | Mounting and battery set up of raspberry pi and working on setting up the github profile for portfolio project planning
|  | Ray | Install OpenCV on rpi. Begin inferencing code on pi
|  | Lingze Meng | According to the demo given by the client, start setting up the virtual machine and install all the resources required for yolov4 to operate
| Collected dataset pre-labeling | Haoge Ming | try to label some images that collected in the dataset by using CVAT