## Sheet1
Week 12 | Tasks | Task Allocation | Notes
| Mentor Meeting | All Team Members | Not happening this week, keep up communication through teams
| Team Portfolio | All Team Members | Continue to contribute / setup the Github
| Team Poster | All Team Members | Start on design of the team poster - get approval from Inviol to use logo
| Finish Scripts | Julia | Finish the connecting to event api script, test on pi
|  | Gamana | Final setup and ordering of body mounting equipments and working on portfolio planning
|  | Ray | Attempt running inference on tensor flow - primarily focussing on final deliverables
|  | Lingze Meng | Fiinish model training and transfer leraning, and indicidual report, also keep working on modify the poster
|  | Haoge Ming | Finish individual work of diagrams composing and try to add more specific on the methodology part in poster. Finally,check if there is any diagrams need to compose as well.