## Sheet1
Week 9 | Tasks | Task Allocation | Notes
| Mentor Meeting | All Team Members | Wednesday - 10:30am
| Team Portfolio | All Team Members | Continue to contribute / setup the Github
| Team Poster | All Team Members | Start drafting background information sections
| Individual Reports | All Team Members | Start drafting individually
| Script writing | Julia | Write script that will call to the Inviol API and excecute the exception logic using shapely
| Learining to make deployment diagram,Github and mounting of camera onto the body and working on portfolio planning | Gamana | Mounting and battery set up of raspberry pi and working on setting up the github profile for portfolio project planning
|  | Ray | complete inference code now that opencv is properly installed and finish mp4 to frames converting script. Also complete script to extract 2-3 fps from videos
|  | Lingze Meng | Through the virtual machine provided by the client, combined with some available datasets we collected before to start train the model and prep files
|  | Haoge Ming | Try to find useable data for training in coco data and fix the data set problem