## Sheet1
Week 8 | Tasks | Task Allocation | Notes
1 | Team Meetings | All Members | Team Meetings to be held on Tuesday (in person) and Thursday (Online).
2 | Update Team Minutes | Julia Borlase
3 | Update Trello Board for Sprint 1 | All Members | To be completed during Tuesdays team meeting
4 | Questions for the Client | All Members | Filling out the document for the 3rd client meeting with questions throughout the week leading up to fridays meeting
5 | Individual Readings on model training and camera - look at open source repositories | All Members | Each member of the team will continue to read into camera models and open source repositories to continue to upskill in the knowledge of model training and gain ideas as to how this will be applied to our project
6 | Mentor Meeting | All Members
7 | Client Meeting | All Members | Client meeting planned for tueday at 2pm was moved to thursday after the client called in sick on tuesday
8 | Scenario Planning Document | All Members | Document to start planning which scenarios will be needed to be captured to begin model training - these will be discussed and added to during the meeting with the client
9 | Weekly Report | All Memebers
10 | Weekly Schedule | All Members
11 | Finalize Camera Hardware Choice | All Members | Based of research done last week and discussion with the client