## Sheet1
Week 11 | Tasks | Task Allocation | Notes
| Mentor Meeting | All Team Members | Wednesday - 10:30am, demo contributions to mentor
| Team Portfolio | All Team Members | Continue to contribute / setup the Github
| Team Poster | All Team Members | Finish draft and send to mentor by Friday 14/10
| Individual Reports | All Team Members | Send drafts to mentor by Friday 14/10
| Finish Scripts | Julia | Finishing connecting to event api script and working to connect with raspberry pi scripts
| Ordering the mounting reqirements for the camera,Camera mounting on boday research and portofolio | Gamana | Learining to make deployment diagram,Github and mounting of camera onto the body and working on portfolio planning
|  | Ray | Complete personal section for end of project deliverables - fix raspberry pi code before handing off to Sai
|  | Lingze Meng | Complete the writing of the Results (What) Project Artefacts in the poster, contact the customer to solve the problem of the weight file in the model training, and complete the draft of personal reflection
| Darwing Diagrams | Haoge Ming | WBS chart & flowchart are completed, trying to compose system block diagram. Mutiple diagrams will be used in poster.