## Sheet1
Risk Register for Inviol Body Camera Project
Prepared by:Haoge Ming |  |  |  |  | Date:03/16/2022
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 |  | Project schedule is not clearly understood/defined | Project schedule may be changed due to the lack of project information (feedback) | Schedule | Bad schedule plan |  | Relaunch the project schedule meeting with project team | Haoge Ming | Low | Moderate | Open
2 |  | Unplanned work that must be accommodated | Project may go through some changes due to unplanned predicament | Cost/Quality | Bad task management or Lack of information of future tasks |  | Communicate to the Project Manager with plan of action, including impact on time, cost and quality | Julia Borlase | Low | High | Open
3 |  | Lack of communication causing delay in project progress and confusion | The project team having issues with communication | Performance | No communication |  | Work it out and correct misunderstandings immediately | Whole team | Moderate | High | Open
4 |  | Breif loss of communication with the mentor | Mentor had to take sick leave, this wasnt communicated with the group so meetings that needed to be held were not |  | Lack of communication |  | Email the mentor and communicate another meeting time | Whole team | Moderate | High | Closed
5 |  | Low performance | Some of the work done may not result in good performance due to poor communication or misunderstandings between team members during the collaboration process | Performance | miscommunication among team members |  | Start detecting during the project planning process any issues that will affect the development schedule during the future collaboration. Develop a schedule and follow the steps closely | Whole team | Moderate | High | Open
6 |  | High Cost | During the development of the project model, it is possible to spend more than the budget for each step of the process. | Cost | Insufficient understanding of the budget required for each future development task |  | The risk of cost reduction needs to be reduced by accurately estimating the cost of each project. As the project enters the development phase, it is recommended to schedule regular reviews of the project budget as well as the project schedule | Whole team | Moderate | Moderate | Open
7 |  | Time crunch | Some tasks in the process are likely to take more time to complete. There is a risk that the project will be carried out with delayed completion of tasks due to improper time allocation | Time/Schedule | Lack of understanding of the content of each task and inability to accurately budget the time spent |  | Consider the lack of time in time for the project planning phase, overestimate the estimated time each character will take and build in time contingencies. Developing a Gantt chart and strictly following the timeline in the chart will keep the entire project on track | Whole team | Moderate | High | Open
8 |  | Scope Risk | Some information about the project development was not clearly communicated to the stakeholders before the project objectives were defined, resulting in the possibility of stakeholders changing requirements during project development | Scope | Lack of communication with all skateholders |  | Carefully confirm project objectives and detailed requirements with all stakeholders during the project preparation phase and agree on all aspects with others prior to project development | Whole team | Moderate | High | Closed